## SAMPLE BUG REPORT
Bug Title | Module | Severity | Priority | Assigned to | Reported By | Environment | Description | Steps To Reproduce | Expected Result | Status | Screenshot (if any)
Customer details are displayed in correct order with wrong keys | Customer | Sev 2 | High | Shashwati,Karthik | Karthik | Pre-Production | Customer details are displayed in correct order with wrong keys | 1. On Postman, fetch request for getting customer details,Details are displayed in correct order but with worong keys (eg: customer id key with clerkId value ) | Correct key value pairs | Resolved
Deleting Loan Application throws an exception | Customer | Sev 2 | Medium | Shashwati | Shashwati | Pre-Production | Deleting any loan application throws error ("no records found") | 1. Deleting a loanapplication is done via postman, method throws exception | Application deletedResolved
Search by date not working | Clerk | Sev 2 | Medium | Karthik | Karthik | Pre-Production | Search by date does not yeild results | 1. Fetch searchByDate in clerk 2. Response does not contain any data | List of all applications by date | Resolved
Loan Repayment is debited even if higher than balance | Customer | Sev 2 | High | Shashwati | Shashwati | Pre-Production | Loan repayment becomes negative when amount debited is higher than balance | 1.Repay loan with amount greater than balance | Error | Resolved
Loan Sanction Button page does not load | Manager | Sev 1 | High | Karthik | Karthik | Production | Loan Sanction page does not load | 1. Open view all loans 2.Click on update pending loans | Option to Approve/Reject loan | Resolved
Vew all loandetails opens browser print option | Manager | Sev1 | High | Shashwati | Shashwati | Production | Opening loandetails page opens print option in browser | 1.Login to manager 2.Open view all loan applicationws | All Loan Applications | Resolved
Sending Mail after loan status change not working | Manager | Sev 1 | Medium | Karthik, Shashwati | Karthik | Production | Mail does not connect to smtp on local system | 1.Login to Manager 2.View all loan applications 3. update status of loan | Mail sent | Unresolved
| Manager | Sev 3 | Medium | Shashwati | Karthik | Pre-Production | Manager can approve pre-approved loan | 1.Login to Manager 2.View all loan applications 3. update status of approved loan | No Data Found | Resolved